# FEMORA — Person 3 Plan (AI, Reports, Deploy and Test)

Your job: the AI calls, content, reports, and then deploying and testing the whole app.

You own the only server code in FEMORA (the AI proxy) and you are the person who deploys and tests the final product. Person 1 and Person 2 fix what you find.

## 1. What you own

- Your folders: api, src/ai, src/reports, content, docs.

- Also yours across the whole project: the Vercel deployment, the environment variables, and the final test passes.

- You do not write: screens (Person 1), or the database, PIN, encryption and safety rules (Person 2).

- Your branch: delivery. Merge to main through a pull request at least every 4 hours.

- Your merge comes second at final integration, right after Person 2's.

## 2. Your tasks by phase

Phase 1: Setup and first deploy (hours 0 to 2)

- Create the GitHub repo, the three branches and the pull request rules.

- Create the Vercel project and deploy a hello page and a /api/ping function. A live link must exist by hour 2.

- Commit .env.example (empty values) and a README skeleton.

- With the other two, write the shared contract and freeze version 1.

Phase 2: Seed data and content format (hours 2 to 6)

- Write the synthetic demo data for all three journeys. Every row has isSample = true.

- Validate it with Person 2's schemas. Person 1's mock functions read the same file.

- Set the content format: one Markdown file per topic, with front matter for topic ID, title, journey, sources and review status (reviewed or pending).

Phase 3: Demo profile (hours 4 to 8)

- The "Try the demo" loader for the sample profile, and its reset button.

- A first draft of the test checklist (section 6), so testing is ready before there is anything to test.

Phase 4: Menstrual Health (hours 6 to 16)

- buildAiPayload() with the Zod whitelist (section 3).

- The /api/ai function with Gemini first and Grok as fallback.

- Menstrual education content, plus the Sexual Wellbeing content, FAQs and glossary. The FAQs sit alongside the other features, not in place of them.

- The in-browser content search with MiniSearch.

Phase 5: Maternity (hours 12 to 22)

- Maternity and postpartum content, each topic with a source.

- The AI payload for maternity.

- generateNotifications(), which runs when the app opens and creates in-app reminders from saved appointments.

Phase 6: Menopause and reports (hours 16 to 26)

- Menopause content.

- Reports for all three journeys with @react-pdf/renderer (section 5).

- First rough integration test at hour 18 (section 6).

Phase 7: Polish (hours 26 to 31)

- The "AI-generated" label, the "What gets sent" preview and the AI on and off toggle (with Person 1).

- A copy review so nothing sounds like a diagnosis.

- Show pending-review content as pending.

Phase 8: Testing (hours 29 to 34)

- Run the full checklist in section 6 and file every bug as a GitHub Issue (section 6).

- Re-test each fix on the live link.

Phase 9: Final deploy and docs (hours 33 to 36)

- Final deploy and a check on a phone and a laptop (section 7).

- Finish the documentation (section 8).

## 3. The AI proxy

- Where: one Vercel serverless function at /api/ai. It is stateless, with no database, and it never logs request bodies.

- Order of calls: Gemini first. If it errors, times out (AI_TIMEOUT_MS) or is rate limited, retry once with Grok. If both fail, return 502 and the app shows the rule-based fallback.

- Whitelist: the request may contain only journey, window, metrics (numbers), symptomIds and contentPassages (reviewed text with IDs). A Zod schema rejects anything else with 400. buildAiPayload() is the only code in the app allowed to call the proxy.

- Never sent: name, nickname, PIN, notes, appointment details, exact dates, or anything from Sexual Wellbeing.

- Limits: a token cap on every reply, a request size limit and a best-effort rate limit per IP.

- Rules in every prompt: no diagnosis, no urgency decisions, never contradict safety guidance, and answer only from the supplied reviewed passages.

- Skip AI for a check-in that raised a safety flag.

- Responses: 200 with { text, provider }, 400, 429, 502, 503 (AI off).

- Provider terms: check each provider's data-use terms. Some free tiers may use requests to improve products, so use a paid or no-training setting for real use and keep demos on sample data.

## 4. Content rules

- Every topic has a credible source and a review status. Check each medical statement against its source before release.

- Anything not yet reviewed is marked pending and shown as pending.

- Write in plain language. Never claim to diagnose.

- Search runs in the browser. Only the retrieved reviewed passages go to the AI, never the whole library.

## 5. Reports

- Separate reports for Menstrual Health, Maternity and Menopause.

- The user picks the period and the sections, and can remove optional sections in the preview.

- The preview and the PDF come from the same <ReportDocument> component.

- Each report shows the journey and the date range it covers.

- Sharing uses the device share sheet, only when the user taps Share. There is no automatic sending and no email integration.

- If generation or download fails, keep the selections and offer a retry.

## 6. Testing (you run it)

When you run it

- Hour 10: type-check on main.

- Hour 18: rough integration on a throwaway branch. List what breaks.

- Hours 28 to 34: the full pass on the live link.

- Hour 34: a final pass after the feature freeze.

How to report a bug

- Open a GitHub Issue with the steps, what you expected, what happened, and the browser.

- Add one label: ui (Person 1), data (Person 2) or ai (you).

- Close it only after you re-test the fix on the live link.

The checklist

- Safety scenarios: each shows the expected rule-based guidance, and the AI never overrides it.

- Profile isolation: two profiles on one device cannot see each other's data.

- PIN and backup: lock, unlock, export, wipe, import.

- Validation: a bad value is rejected and the form keeps what was typed.

- Saving: "saved" appears only after a real save. A full or locked store shows the retry message.

- AI fallback: switch AI off, then break the Gemini key (Grok should answer), then break both (rule-based fallback).

- What leaves the device: in the network tab, only whitelisted numbers and labels reach /api/ai. An extra field returns 400.

- Reports: each journey previews and downloads from saved records.

- Sharing: nothing is shared without a tap.

- Privacy: no health data on public pages, and none in logs.

- Labels: sample data and AI output are clearly labelled.

- Layouts: desktop and mobile, with a basic tablet check, in light and dark themes.

- Accessibility: keyboard navigation, focus, labels and contrast.

- Browsers: Chrome and Safari at minimum.

- Judge walkthrough: open the live link in a fresh browser and complete the main journey without help.

## 7. Deployment

- Hosting: Vercel for the static app and the /api/ai function.

- Environment variables (server only): GEMINI_API_KEY, XAI_API_KEY, AI_PRIMARY_MODEL, AI_FALLBACK_MODEL, AI_ENABLED, AI_TIMEOUT_MS, AI_MAX_TOKENS, AI_RATE_LIMIT_PER_MIN.

- Environment variables (build time): VITE_AI_ENDPOINT (/api/ai), VITE_APP_ENV, VITE_USE_MOCKS (false for the real deploy).

- Keys never reach the browser. Never commit real keys.

- Redeploy after every merge to main and re-test on the live link, not only on a laptop.

- Final deploy checklist: HTTPS works, the demo profile loads and resets, /api/ai answers, the fallback works with AI off, and the link opens from a phone.

- Wake-up: open the live link a few minutes before judging so everything is warm.

## 8. Documentation you deliver

- README with setup and deployment steps.

- Feature-status checklist (done, partial, simulated).

- Architecture and data-flow overview.

- Environment configuration guide.

- Testing and known-limitations checklist, including that data lives in one browser, that Safari may clear site data, and that profiles are not a security boundary without a PIN.

## 9. Done when

- The live HTTPS link works from a fresh browser and a phone.

- All checklist items pass, and known issues are written down.

- Reports preview and download correctly.

- The Gemini, Grok and rule-based fallbacks all work.

- The repo is shared with complete documentation.